## Sheet2
| Yearly plan 2022 | Project | Duration
|  | Deployment of CI/CD Pipeline | 09.04.22 to 12.31.22
Week in a year | Start date | End date | Tasks | Sprint | Difficulty (1 to 3) | Version
1 | 2022-09-04 | 2022-09-06 | Investigate and gather Documentation | Sprint 1 | 1
2 | 2022-09-07 | 2022-09-10 | Design overall System Architecture | Sprint 2 | 2
3 | 2022-09-11 | 2022-09-14 | Setup a basic project structure | Sprint 3 | 2
4 | 2022-09-15 | 2022-09-18 | Implement a basic source code | Sprint 4 | 2
5 | 2022-09-19 | 2022-09-22 | Create and run tests locally | Sprint 5 | 2
6 | 2022-09-23 | 2022-09-29 | Review current impletation | Sprint 6 | 1
7 | 2022-09-30 | 2022-10-06 | Write documentation | Sprint 7 | 1
8 | 2022-10-07 | 2022-10-13 | Setup GitHub Actions | Sprint 8 | 3
9 | 2022-10-14 | 2022-10-20 | Deploy source code to Azure App Service | Sprint 9 | 3
10 | 2022-10-21 | 2022-10-27 | Connect Github with Azure Pipelines | Sprint 10 | 2
11 | 2022-10-28 | 2022-11-03 | Review current impletation | Sprint 13 | 1
12 | 2022-11-04 | 2022-11-10 | Update CI/CD pipeline | Sprint 18 | 2
13 | 2022-11-11 | 2022-11-17 | Write documentation | Sprint 19 | 1
14 | 2022-11-18 | 2022-11-24 | Gather metrics | Sprint 20 | 1
15 | 2022-11-25 | 2022-12-01 | Bug fixing | Sprint 22 | 2
16 | 2022-12-02 | 2022-12-08 | Bug fixing | Sprint 23 | 1
17 | 2022-12-09 | 2022-12-15 | Write user manual | Sprint 24 | 1
18 | 2022-12-16 | 2022-12-22 | Write release notes | Sprint 25 | 1
Formulas:
Yearly plan 2022 = [Project, row above]+1
Project = [Yearly plan 2022]+3